## Sheet1
Time Line
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Requirement Analysis | Week 1: March 5 – 18
System Design | Week 3: March 19 – April 1
Development | Week 5: April 2 – May 6
Testing | Week 6: April 8 – May 13
Requirement Analysis | Week 1: System Design; Week 2: Development; Week 3: Testing
Project Proposal | Week 1: Technology selection; Week 2: Front End; Week 3: Unit Testing
Srs document | Week 1: System Architecture; Week 2: Back End; Week 3: Integration Testing
| Database Design | Database | System Testing
UX/UI Design
System Modules
Logic Design
Test Plan
Front End | Week 1: React Js
Back End | Week 1: Node Js
Date Base | Week 1: MongoDB
Version control | Week 1: Git & Git Hub